## testing
report | severity | title | date_opened | reported_by | problem | assigned_to | date_fixed | changes_made | verified_by
1 | 3 | Screen scaling issue | 2017-11-26 06:15 | testing team | On my laptop the Contributions table was missing the bottom two buttons. The GUI should have some dynamic scaling implemented or at least a scrolling feature so I can scroll down and see the buttons.
2 | 4 | Live updates | 2017-11-26 06:38 | testing team | When i added a Donor who made a contribution but did not exist, i had to re launch the program to be able to enter his/her contribution because the envelope number was not immediately available. | Cavaughn Browne | 2017-11-29 | now update without having to restart the app | testing team
3 | 4 | Display numbers with 2 decimals in Contribution Table | 2017-11-26 06:45 | Mrs. Wuthrich | In the contribution table, whole numbers are displayed without a .00 at the end. A tutorial on how to solve this is posted in the wiki. | Max Duhan | 2017-11-29 | amt now always displays with 2 decimal places and right justifies
4 | 4 | resetting fields to empty | 2017-11-26 06:56 | testing team | on the donors table it would be nice if the fields reset automatically to empty after adding or updating, without having to hit the reset button. | johann redhead | 2017-11-28 | fields now reset with default values | testing team
5 | 2 | Mail preference electronic without an email address. | 2017-11-26 07:00 | testing team | On the donors table you can insert a new donor without an email address, but with their mail_pref set to electronic.(See env_num 347) | Cavaughn Browne | 2017-11-28 | Now you cannot add donor with an electronic mail preference without an email address | testing team
6 | 4 | pressing numbers while in envelope id selector | 2017-11-26 07:21 | testing team | on the contributions table, when selecting enevelope id, pressing numbers will simply concatenate them onto the 0 that is default in the field. Pressing numbers should scroll you to a value starting with that number in the envelope id list.
7 | 4 | date defaulting in contributions | 2017-11-26 07:30 | testing team | On the contributions table, it might be easier if date defaulted to the previously entered date. The user might not be inserting all data on the same day the donations are received. | Cavaughn Browne
8 | 4 | contributions table fund not defaulting after add | 2017-11-26 07:44 | testing team | on the contributions table, after pressing add, every field reverts back to their default except for fund. Fund still stays on last input fund. It would be nice if it defaulted back to General, since most donations seem to be towards General. | Zac Conley | 2017-11-28 | Defaults Fund Field to general | testing team
9 | 2 | update broken on contributions | 2017-11-26 07:53 | testing team | on the contributions table, I selected donation id 202 and tried to change the date to 2017-11-12. An error popped up saying Unknown column date in field list. And the date was not changed. | Zac Conley | 2017-11-28 | Fixed update button for contribution frame | testing team
10 | 3 | clicking contribution doesn't do anything | 2017-11-26 07:56 | testing team | on the contributions table, I scrolled down and clicked ID 218. The only thing that changed in the fields below is the 'Fund' field. This happens to multiple tuples at the bottom of the table. | Cavaughn Browne | 2017-11-29 | Now clicking on a record will change the appropriate field below. Also fixes TAR 11 | testing team
11 | 3 | clicking contribution doesn't do anything cont. | 2017-11-26 07:59 | testing team | cont. When clicking a tuple where nothing happens, netbeans console shows : Exception in thread 'AWT-EventQueue-0' java.lang.IllegalArgumentException: setSelectedIndex: 315 out of bounds | Cavaughn Browne | 2017-11-29 | Tar 10 was the culprit | testing team
12 | 2 | funds update not working | 2017-11-26 08:01 | testing team | When I tried to change a quick books account number and press update, an error popped up saying 'unknown column qb_acc in field list' | Abdullah Alathel | 2017-11-28 | fixed FundDAO.updateFund | testing team
13 | 2 | donors update not working | 2017-11-26 08:04 | testing team | When I made an edit to a student's first name and pressed Update, nothing happened. | Abdullah Alathel | 2017-11-27 | linked update button to function,fixed DonorDAO.updateDonor | testing team
14 | 3 | sorting breaks donors field filling | 2017-11-26 09:45 | testing team | In the donors table, when you sort by anything that isn't env_num increasing, clicking on a tuple will fill the fields below with incorrect values | Johann Redhead | 2017-11-28 |  | testing team
15 | 2 | Contribution delete button | 2017-11-26 16:44 | testing team | In the contribution frame, the delete button seems to have no functionality. It neither deletes the tuple in the frame, nor the database. | Chris Cook | 2017-11-30 | used the hidden text field to get the ID of the cont.
16 | 3 | Stuck in Amount | 2017-11-26 19:48 | testing team | When you click on amount in the the contribution table you get stuck and cant click out. | testing team | 2017-11-28 | We have made the cells in the Contribution frame un-editable. | testing team
17 | 2 | Contribution Frame duplicate value into note column | 2017-11-26 20:06 | testing team | In the Contribution frame, when you click into the type field, then click into the note field, the string in type is then duplicated to the note field. | testing team | 2017-11-28 | We have made the cells in the Contribution frame un-editable. | testing team
18 | 4 | Donor Col Names | 2017-11-26 20:11 | testing team | Column names need to user friendly | testing team | 2017-11-28 | Changed the column names on the table model to more user friendly names. | testing team
19 | 3 | Stuck in Env Num | 2017-11-26 20:14 | testing team | Clicking into the Envelope Number in the contribution tables causes you to get stuck. | testing team | 2017-11-28 | We have made the cells in the Contribution frame un-editable. | testing team
20 | 3 | Cont.Table Double Click Edit | 2017-11-26 20:24 | testing team | Donor and Fund tables dont allow double clicking fields in order to edit, but contribution does. Making contribution not double clickable might help fix the other errors about getting stuck | testing team | 2017-11-28 | We have made the cells in the Contribution frame un-editable. | testing team
21 | 4 | Error codes. IE primary key error | 2017-11-26 20:30 | testing team | User friendly error codes. Not programmer error messages on Contribution and Donor Frames | Clarence Williams | 2017-11-30 | More user friendly error messages displayed in Donor and Contribution frames
22 | 4 | Type col in contribution | 2017-11-26 20:35 | testing team | the types are not capitalized for example, coin should be Coin. At the bottom of the screen where the fields are the types are captialzied. | Max Duhan | 2017-11-29 | Fully fixed now, capitalizes the non-acronym words and all caps the ACH acronym | testing team
23 | 2 | Wrong Date rollovers | 2017-11-26 20:49 | testing team | Entering an invalid date (2017-11-67) causes the program to insert the date that is 67 days from the current date | Clarence Williams | 2017-11-29 | Date format's lenient property was sent to false, which imposes strict parsing on date variables | testing team
24 | 4 | Select any button with focus by pressing Enter | 2017-11-27 20:15 | Wuthrich | When focus is on a button, the user should be able to press the Enter key on the keyboard instead of having to use the mouse and click on the button. | Tellon Smith | 2017-11-29 | All buttons in the program can be selected by pressing Enter when it has focus. | Wuthrich 11/30 Pull Req 90
25 | 4 | Wrong label on Donor | 2017-11-27 20:31 | Wuthrich | On the Donor form, the label for the mail preference combo box should be Statement Preference | Kevin Lord | 2017-11-29 | Kevin fixed the arrangement, but it defaulted back after clicking design view in netbeans.
26 | 4 | Email Address text field | 2017-11-27 21:02 | Wuthrich | On the Donor form, the email addres field isn't long enough to hold most email addresses. Make it longer (and adjust layout of other fields if necessary to keep things aligned) | Zaineb Ramzan
27 | 4 | Action after Reset (Donors and Funds) | 2017-11-27 21:08 | Wuthrich | On both the Donor and Fund forms, if the user presses the Reset button, text fields are appropriately cleared. At this point, the Fund Name text field (or First Name field on Donors) should have focus and the cursor should be blinking in that field. | Zac Conley | 2017-11-29 | Fields are now focused after resets | Wuthrich 11/30
28 | 4 | Up and Down arrows in tables | 2017-11-28 14:53 | Wuthrich | When the user clicks on a row in a table, the text fields below should populate correctly. If the user uses the up or down arrows to navigate in the table, the text fields should re-populate accordingly | Tellon Smith | 2017-11-29 | Text fields on all frames now re-populate with selected row when the up and down arrows are used. | Wuthrich 11/30
29 | 3 | Disable Add Button | 2017-11-28 22:10 | Wuthrich | On contribution and donor frames, when a row is selected in the table, the Add button should be disabled | Kevin Lord | 2017-11-30 | Add button is set to disable when table row is clicked
30 | 1 | Contributions update needs fixing | 2017-11-29 18:26 | Cavaughn Browne | ***Marked as duplicate of TAR 9 by Wuthrich*****Contributions update doesn't work | Tellon Smith | 2017-11-29 | update button on contribution frame now works