## Project Timeline
PROJECT TIMELINE
| ENTER START DATE: | 2017-10-23
Id | ACTIVITY | START | END | NOTES | Column1
-26 | Project Start | 2017-10-23 | 2017-12-06
-25 | GitHub repository created | 2017-10-23 | 2017-10-25 |  | Cavaughn
-24 | DB created | 2017-10-23 | 2017-10-25 |  | KDT
-23 | DB populated | 2017-10-23 | 2017-10-27 | 11/3/2017 Include all funds. Change all dates to 1/1/2017 or later. Make most amounts less than $300.00 and make most a whole number of dollars. Notes are rare. Delete most notes. | MZ
-22 | Core-Fund | 2017-10-23 | 2017-10-27 |  | MZ
-21 | Core-Donor | 2017-10-23 | 2017-10-27 |  | MZ
-20 | Core-Contribution | 2017-10-23 | 2017-10-27 |  | TDK
-19 | TestingDB created | 2017-11-01 | 2017-11-03 |  | Schenkl
-18 | MainFrame ver 1 | 2017-10-23 | 2017-11-03 |  | VCJ
-17 | DonorFrame ver 1 | 2017-10-23 | 2017-11-03 | Tables, labels, text fields, buttons in place | CK
-16 | FundFrame ver 1 | 2017-10-23 | 2017-11-03 | Tables, labels, text fields, buttons in place | TJ
-15 | ContributionFrame ver 1 | 2017-10-23 | 2017-11-03 | Tables, labels, text fields, buttons in place | VCJ
-14 | DAO files | 2017-10-23 | 2017-11-03 |  | Silva
-13 | FundTableModel | 2017-10-23 | 2017-11-08 | Columns should have correct titles, be in order, and cells of a table should be editable. | Travis
-12 | DonorTableModel | 2017-10-23 | 2017-11-08 | Columns should have correct titles, be in order, and cells of a table should be editable. | Travis
-11 | ContributionTableModel | 2017-10-23 | 2017-11-08 | Columns should have correct titles, be in order, and cells of a table should be editable. | TDK
-10 | Report Frame ver1 | 2017-10-23 | 2017-11-10 |  | Cavaughn
-9 | Splash Screen | 2017-10-27 | 2017-11-10 |  | CK
-8 | Login Screen | 2017-10-27 | 2017-11-10 | Get the 4 parameters for making a DB connection (using constructor in DBConnection), establish the connection, and pass the connection object as a parameter to the ContributionFrame, DonorFrame, and FundFrame. Window should be centered. Default first 2 fields to "griffincomplaints.xyz" and "money". Place Focus on database name field. | CK
-7 | ContributionFrame Ver 2 | 2017-11-04 | 2017-11-13 | Table reflects contents of DB and is sortable, editable. Text fields are laid out nicely in the correct order, default if applicable, and combo boxes are appropriately filled. | VCJ
-6 | DonorFrame Ver 2 | 2017-11-04 | 2017-11-13 | Table reflects contents of DB and is sortable, editable. Text fields are laid out nicely in the correct order, default if applicable, and combo boxes are appropriately filled. | CK
-5 | FundFrame Ver 2 | 2017-11-04 | 2017-11-13 | Table reflects contents of DB and is sortable, editable. Text fields are laid out nicely in the correct order, default if applicable, and combo boxes are appropriately filled. | TJ
-4 | Add Buttons | 2017-11-03 | 2017-11-15 |  | Abdullah
-3 | Delete Buttons | 2017-11-03 | 2017-11-15 |  | Chris Cook
-2 | Update Buttons | 2017-11-03 | 2017-11-15 |  | Zac
-1 | ContributionFrame Ver 3 | 2017-11-13 | 2017-11-20 | Default Fund field. Initial focus on Envelope ID field (instead of date). Edit Fund field. Name field non-editable and non-focusable. Populate fields when row is selected (after sorting). Length fund text field
0 | DonorFrame Ver 3 | 2017-11-13 | 2017-11-20 | Issues not fixed in Version 2. Tab order. Edit City field. Prevent entry of > 2 characters in State field. When Add button is selected, last name is not being inserted correctly. Clear text fields after an add. Table needs scroll bar.
1 | FundFrame Ver 3 | 2017-11-13 | 2017-11-20 | Clear fields after successful "Add". Be able to just hit Enter key when any button has focus instead of having to use the mouse.
2 | Report Buttons | 2017-10-23 | 2017-11-22 |  | Cavaughn
3 | Testing | 2017-11-06 | 2017-12-06 |  | Everyone
4 | Formal Testing | 2017-11-27 | 2017-12-03 |  | KDT & Schenk
5 | Project End | 2017-12-06
Formulas:
END = Activities[[#This Row],[START]]+2
START = [START, row above]+10

## calcs (hidden)
*** This sheet should remain hidden ***
|  | Today: | 2017-11-13
5
|  | # of rows | 32
#N/A
#N/A
#N/A
|  | Window Activities: | 8 | #N/A
|  |  | 9 | #N/A
|  |  | 1 | #N/A
#N/A
#N/A
#N/A
|  |  |  | -26 | #N/A
|  |  |  | -1 | -26
|  |  |  | 0 | -1
|  |  |  | 1 | 0
|  |  |  | 2 | 1
|  |  |  | 3 | 2
|  |  |  | 4 | 3
|  |  |  | 5 | 4
|  |  |  | #N/A | 5
|  | Calc Window Start | 2017-11-18
|  | Offset | 26
|  | Start | 2017-10-23
|  | Window | 30
Position | Series | Activity Id | Activity | 2017-11-18 | 2017-11-19 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-25 | 2017-11-26 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01 | 2017-12-02 | 2017-12-03 | 2017-12-04 | 2017-12-05 | 2017-12-06 | 2017-12-07 | 2017-12-08 | 2017-12-09 | 2017-12-10 | 2017-12-11 | 2017-12-12 | 2017-12-13 | 2017-12-14 | 2017-12-15 | 2017-12-16 | 2017-12-17 | 2017-12-18
11.3 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
10.3 | 2 | -26 | Project Start | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
9.3 | 3 | -1 | ContributionFrame Ver 3 | 9.3 | 9.3 | 9.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8.3 | 4 | 0 | DonorFrame Ver 3 | 8.3 | 8.3 | 8.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7.3 | 5 | 1 | FundFrame Ver 3 | 7.3 | 7.3 | 7.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6.3 | 6 | 2 | Report Buttons | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
5.3 | 7 | 3 | Testing | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4.3 | 8 | 4 | Formal Testing | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3.3 | 9 | 5 | Project End | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | 2017-11-18 | 2017-11-19 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-25 | 2017-11-26 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01 | 2017-12-02 | 2017-12-03 | 2017-12-04 | 2017-12-05 | 2017-12-06 | 2017-12-07 | 2017-12-08 | 2017-12-09 | 2017-12-10 | 2017-12-11 | 2017-12-12 | 2017-12-13 | 2017-12-14 | 2017-12-15 | 2017-12-16 | 2017-12-17
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | -26 | PROJECT START | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | -1 | CONTRIBUTIONFRAME VER 3 | #N/A | #N/A | 9.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 0 | DONORFRAME VER 3 | #N/A | #N/A | 8.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 1 | FUNDFRAME VER 3 | #N/A | #N/A | 7.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 2 | REPORT BUTTONS | #N/A | #N/A | #N/A | #N/A | 6.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 3 | TESTING | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 4 | FORMAL TESTING | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 5 | PROJECT END | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | 2017-11-18 | 2017-11-19 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-25 | 2017-11-26 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01 | 2017-12-02 | 2017-12-03 | 2017-12-04 | 2017-12-05 | 2017-12-06 | 2017-12-07 | 2017-12-08 | 2017-12-09 | 2017-12-10 | 2017-12-11 | 2017-12-12 | 2017-12-13 | 2017-12-14 | 2017-12-15 | 2017-12-16 | 2017-12-17
|  |  | Current Day | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2017-11-01 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | Nov 2017 - Top Band | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2017-12-01 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  |  | Dec 2017 - Top Band | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
|  |  | 2017-11-02 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2017-12-02 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  |  | 3 | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN
|  |  |  | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
|  |  |  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17